## PMR
DEPERTMENT OF EDUCATION - GINGOOG CITY DIVISION | [11 empty] | Procurement Monitoring Report as of June 30, 2026
(2nd Semester for FY 2025)
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Actual Procurement Activities | [19 empty] | Source of Funds | ABC (PhP) |  |  | Contract Cost (PhP) |  |  |  | List of Invited Observers | Date of Receipt of Invitation
[5 empty] | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance |  | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance |  | Pre-bid Conf4 | Eligibility Check5 | Sub/ Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column1 | Column2
COMPLETED PROCUREMENT ACTIVITIES | [31 empty] | -
| EQUIPMENT for the Replacement to the old unit used by the Canvasser in the performance of procurement related functions | LEGAL UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-05 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-24 | 2026-02-24 | Government of the Philippines (current year's budget) | 43900 | 43900 | 0 | 43900 | 43900 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-24 | Completed | Pre-Bid | Failed | Division MOOE | OSEC-10-25-00640
| EQUIPMENT for the Replacement to the old unitand damaged IT Equipments in Supply unit | Supply Office | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-05 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-06 | 2026-03-06 | Government of the Philippines (current year's budget) | 12000 | 12000 | 0 | 9600 | 9600 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-06 | Completed |  |  | DCP FUND 2024/SUB- ARO-10-24-543 | OSEC-10-25-00640
| FOOD STUFF for the Conduct of the Weekly Division executive Committee Meeting in January- March 2026, 8:30 am at the Division Conference Hall | SGOD-SEPS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-05 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-04-30 | 2026-04-30 | Government of the Philippines (current year's budget) | 45000 | 45000 | 0 | 45000 | 45000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | Completed | Pre-Bid | Failed | Division MOOE | Division MOOE
| FUEL for the Consumption for the month of January- March 2026 | Supply Office | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-12 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-05-05 | 2026-05-05 | Government of the Philippines (current year's budget) | 149946 | 149946 | 0 | 143232 | 143232 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-05 | Completed | Pre-Bid | Failed | HRD Fund | Division MOOE
| DRINKING WATER for the Consumption for the month of January- March 2026 | Supply Office | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-12 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-31 | 2026-03-31 | Government of the Philippines (current year's budget) | 9000 | 9000 | 0 | 9000 | 9000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-31 | Completed | Pre-Bid | Failed | Div. MOOE 2024 -OSEC-10-24-6471 | Division MOOE
| FOOD STUFF for the Division Seminar Workshop on Mind Matters: A Gender Responsive Mental Health and Wellness Workshop | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-12 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-19 | 2026-02-19 | Government of the Philippines (current year's budget) | 256000 | 256000 | 0 | 256000 | 256000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-19 | Completed | Pre-Bid | Failed | Div. MOOE 2024 -OSEC-10-24-6471 | GAD Continuing
| SUPPLIES for the Division Seminar Workshop on Mind Matters: A Gender Responsive Mental Health and Wellness Workshop | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-12 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-21 | 2026-01-21 | Government of the Philippines (current year's budget) | 28000 | 28000 | 0 | 27421 | 27421 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-21 | Completed | Pre-Bid | Failed | Division MOOE | GAD Continuing
| TARPAULIN for the Division Seminar Workshop on Mind Matters: A Gender Responsive Mental Health and Wellness Workshop | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-12 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-22 | 2025-09-22 | Government of the Philippines (current year's budget) | 1000 | 1000 | 0 | 1000 | 1000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2025-09-22 | Completed |  |  | Division MOOE | GAD Continuing
| EQUIPMENT for the Archery Target Face | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-12 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-01-22 | 2025-07-25 | Government of the Philippines (current year's budget) | 4944 | 4944 | 0 | 4944 | 4944 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-01-12 | Completed | Pre-Bid | Failed | Div. MOOE 2024 Continuing- 0SEC-10-24-6471 | Sports Fund
| for the Orientation and Workshop on Regional Information Systems (Document Tracking System, Inventory System, and Learning Tracking System | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-21 |  | N/A | N/A | N/A | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-19 | 2026-03-19 | Government of the Philippines (current year's budget) | 204000 | 204000 | 0 | 204000 | 204000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-19 | Completed | Opening of Bids | Failed | TVL Fund 2024 | SUB-ARO-10-25-725
| SUPPLIES for the Student Leaders Forum: Sthrenghtening Communication, Digital Leadership, and School Community Resilience | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-21 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-02-10 | 2026-02-10 | Government of the Philippines (current year's budget) | 9205 | 9205 | 0 | 9205 | 9205 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-10 | Completed | Opening of Bids | Failed | TVL Fund 2024 | SUB-ARO-10-25-725
| PRINTING for the Multigrade Teaching and Learning Resources | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-26 |  | N/A | N/A | N/A | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-03-24 | 2026-03-24 | Government of the Philippines (current year's budget) | 114900 | 114900 | 0 | 114450 | 114450 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-24 | Completed | Opening of Bids | Failed | TVL Fund 2024 | LAA-10-25-696
| PRINTING for the Multigrade Teaching and Learning Resources | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-26 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-24 | 2026-03-24 | Government of the Philippines (current year's budget) | 91100 | 91100 | 0 | 90200 | 90200 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-24 | Completed |  |  | TVL Fund 2024 | LAA-10-25-696
| MATERIALS for the Multigrade Teaching and Learning Resources | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-26 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-06 | 2026-05-06 | Government of the Philippines (current year's budget) | 8700 | 8700 | 0 | 8700 | 8700 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | Completed |  |  | LAA-10-24-344 | LAA-10-25-696
| EQUIPMENT for the School Division Office Payroll Processing | PAYROLL | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-26 |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A |  |  | 2026-06-22 | 2026-06-22 | Government of the Philippines (current year's budget) | 7931 | 7931 | 0 | 6750 | 6750 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-22 | Completed | Pre-Bid | Failed | Sports Fund | Division MOOE 2025
| EQUIPMENT for the School Division Office Payroll Processing | PAYROLL | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-26 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 44699 | 44699 | 0 | 43900 | 43900 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | School MOOE | School MOOE
| SUPPLIES for the School Division Office Payroll Processing | PAYROLL | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-29 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 21900 | 21900 | 0 | 21760 | 21760 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | Sports Fund | Division MOOE
| FOOD STUFF for the Enhancement Training for RSPC Coach and Journalist Qualifiers | CID- EPS | No | NP-53.9 - Small Value Procurement | N/A | 2026-01-29 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-02-13 | 2026-02-13 | Government of the Philippines (current year's budget) | 250000 | 250000 | 0 | 250000 | 250000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-13 | Completed |  |  | Sports Fund | Division MOOE Continuing
| EQUIPMENT for the Internet Connection in the Division Office- | IT | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-09 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-10 | 2026-03-10 | Government of the Philippines (current year's budget) | 7200 | 7200 | 0 | 6948 | 6948 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-10 | Completed |  |  | Sports Fund | DO MOOE Continuing
| FOOD STUFF AND ACCOMMODATION for the Capacity Building on Gender and Development (GAD) Planning and Budgeting and Training on Harmonized Gender and Development Guidelines (HGDG) for GFPS Members as Validators | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-09 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-02 | 2026-03-02 | Government of the Philippines (current year's budget) | 630000 | 630000 | 0 | 630000 | 630000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-02 | Completed |  |  | Sports Fund | GAD FUND REG. FEE
| SUPPLIES for the Capacity Building on Gender and Development (GAD) Planning and Budgeting and Training on Harmonized Gender and Development Guidelines (HGDG) for GFPS Members as Validators | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-09 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-04 | 2026-03-04 | Government of the Philippines (current year's budget) | 41550 | 41550 | 0 | 41550 | 41550 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-04 | Completed |  |  | Sports Fund | GAD FUND REG. FEE
| TARPAULIN for the Capacity Building on Gender and Development (GAD) Planning and Budgeting and Training on Harmonized Gender and Development Guidelines (HGDG) for GFPS Members as Validators | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-09 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-02 | 2026-03-02 | Government of the Philippines (current year's budget) | 1000 | 1000 | 0 | 1000 | 1000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-02 | Completed |  |  | Sports Fund | GAD FUND REG. FEE
| MATERIALS for the EECD Assessment Tool, Literacy, The Thinking and Mathematics Kit for Kindergarten Learners | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-10 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-25 | 2026-03-25 | Government of the Philippines (current year's budget) | 114960 | 114960 | 0 | 114960 | 114960 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-25 | Completed |  |  | Division MOOE | SUB ARO-10-25-612
| SUPPLIES for the Photocopier tonner and fusing for CID Operations | EPS-CID | No | Direct Contracting | N/A | 2026-02-10 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-09 | 2026-03-09 | Government of the Philippines (current year's budget) | 44000 | 44000 | 0 | 43495 | 43495 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-09 | Completed |  |  | Division MOOE | DO MOOE
| SUPPLIES for the 5th AnItem No. 1-5, and 7 for Lei and token for Guest niversarry Celebration of the Schools Division of Gingoog City on March 6, 2026. | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-13 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-11 | 2026-03-11 | Government of the Philippines (current year's budget) | 35250 | 35250 | 0 | 30000 | 30000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-11 | Completed |  |  | Division MOOE | MOOE Continuing Funds
| MEDICAL AND DENTAL SUPPLIES for the Northern Mindanao Regional Athletic Association (NMRAA) Meet 2026- | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-13 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-11 | 2026-03-11 | Government of the Philippines (current year's budget) | 349160 | 349160 | 0 | 309634 | 309634 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-11 | Completed |  |  | LAA-10-24-344 | Sports Funds
| /MATERIALS for the Administrative Officer V Operations | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-20 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-04 | 2026-03-04 | Government of the Philippines (current year's budget) | 70999 | 70999 | 0 | 67550 | 67550 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-04 | Completed |  |  | MOOE 2024 Continuing- OSEC-10-24-6471 | DO MOOE
| Procurement MATERIALS for the Enhancement of the Division Museum- EPS Balagulan | ACCOUNTING | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-20 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-04 | 2026-03-04 | Government of the Philippines (current year's budget) | 3720 | 3720 | 0 | 3720 | 3720 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-04 | Completed |  |  | SNED Fund 2024 | DO MOOE Continuing
| SUPPLIES for the Toiletries for NMRAA 2026 | CID-PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-20 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-04 | 2026-03-04 | Government of the Philippines (current year's budget) | 50000 | 50000 | 0 | 50000 | 50000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-04 | Completed |  |  | SNED Fund 2024 | Sports Fund/
| SUPPLIES for the 1st Quarter of 2026 for COA use | COA | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-20 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-13 | 2026-04-13 | Government of the Philippines (current year's budget) | 13726.92 | 13726.92 | 0 | 12157 | 12157 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-13 | Completed |  |  | SNED Fund 2024 | DO MOOE
| EQUIPMENT AND MATERIALS for the In house printing, binding and delivery of Structured, Pedagogy Lesson Guides and Learning Packets | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-23 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-13 | 2026-04-13 | Government of the Philippines (current year's budget) | 83499 | 83499 | 0 | 78880 | 78880 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-13 | Completed |  |  | Division MOOE | 2025 TBIMS
| SUPPLIES for the Budget and Accounting Office | ACCOUNTING | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-23 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-22 | 2026-04-22 | Government of the Philippines (current year's budget) | 9680 | 9680 | 0 | 9680 | 9680 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-22 | Completed |  |  | Division MOOE | DO MOOE
| SUPPLIES for the Office of the SDS- 1st Quarter CY 2026 | SDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-23 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-22 | 2026-04-22 | Government of the Philippines (current year's budget) | 11423.96 | 11423.96 | 0 | 11423.96 | 11423.96 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-22 | Completed |  |  | Division MOOE | DO MOOE
| SUPPLIES for SGOD Office | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-24 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-10 | 2026-03-10 | Government of the Philippines (current year's budget) | 9600 | 9600 | 0 | 9535 | 9535 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-10 | Completed |  |  |  | DO MOOE
| SUPPLIES of Budget & Accounting Office | ACCOUNTING | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-24 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-10 | 2026-03-10 | Government of the Philippines (current year's budget) | 74246.42 | 74246.42 | 0 | 66021 | 66021 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-10 | Completed |  |  | DRRM | DO MOOE
| FOOD STUFF for the Participants of CY 2025 Audit Exit Conference | ACCOUNTING | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-24 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-02-26 | 2026-02-26 | Government of the Philippines (current year's budget) | 27000 | 27000 | 0 | 27000 | 27000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-02-26 | Completed |  |  | DRRM | DO MOOE
| MATERIALS for the Division Wide Learners Contest in Celebration of the 50th Founding Anniversary of DepEd Gingoog City | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-26 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-17 | 2026-03-17 | Government of the Philippines (current year's budget) | 4550 | 4550 | 0 | 4550 | 4550 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-17 | Completed |  |  |  | Division MOOE Continuing
| SUPPLIES for the Schools Division Office Payroll Processing | PAYROLL | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-26 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-17 | 2026-03-17 | Government of the Philippines (current year's budget) | 49789.93 | 49789.93 | 0 | 48625 | 48625 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-17 | Completed |  |  | DIVISION MOOE | School MOOE
| SUPPLIES for the ASDS Office Supplies | ASDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-26 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-30 | 2026-04-30 | Government of the Philippines (current year's budget) | 15808.46 | 15808.46 | 0 | 5314 | 5314 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | Completed |  |  | DIVISION MOOE | DIVISION MOOE
| FOOD STUFF for the Launching of the 2026 National Women’s Month Celebration and the DepEd GAD Website Center Members as Validators | PSDS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-27 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-06 | 2026-03-06 | Government of the Philippines (current year's budget) | 43450 | 43450 | 0 | 43450 | 43450 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-06 | Completed |  |  | DIVISION MOOE | SCHOOL & DO MOOE
| POLO SHIRT for the Launching of the 2026 National Women’s Month Celebration and the DepEd GAD Website Center Members as Validators | PSDS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-27 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-10 | 2026-03-10 | Government of the Philippines (current year's budget) | 172500 | 172500 | 0 | 172500 | 172500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-10 | Completed |  |  | GAD 2024 | SCHOOL & DO MOOE
| TARPAULIN for the SDO Division 50th Anniversary Celebration on March 3 &6, 2026 | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-27 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-11 | 2026-03-11 | Government of the Philippines (current year's budget) | 7440 | 7440 | 0 | 7440 | 7440 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-11 | Completed |  |  | MOOE 2024 | Division MOOE Continuing
| FOOD STUFF for the WASH in Schools (WinS) Validation of Report SY. 2025-2026 | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-02-27 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-12 | 2026-03-12 | Government of the Philippines (current year's budget) | 28800 | 28800 | 0 | 28800 | 28800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-12 | Completed |  |  | MOOE 2024 | LAA-10-25-645
| FOOD STUFF for the Tree Planting and New Division Office Tour | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-02 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-03 | 2026-03-03 | Government of the Philippines (current year's budget) | 60750 | 60750 | 0 | 60750 | 60750 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-03 | Completed |  |  | MOOE 2024 | DPRP FUND
| FOOD STUFF for the Conduct of the Division Management Committee Meeting in March 2026 | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-02 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-11 | 2026-03-11 | Government of the Philippines (current year's budget) | 84000 | 84000 | 0 | 84000 | 84000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-11 | Completed |  |  | MOOE 2024 | DO & SCHOOL
| MATERIALS for the 50TH Anniversary Celebration of the Schools Division of Gingoog City | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-03 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-06 | 2026-03-06 | Government of the Philippines (current year's budget) | 16800 | 16800 | 0 | 16800 | 16800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-06 | Completed |  |  | GAD 2024 | DO MOOE Continuing
| SUPPLIES for the 1st Quarter CY 2026 for BAC Office | LEGAL UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-03 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-13 | 2026-04-13 | Government of the Philippines (current year's budget) | 15295.67 | 15295.67 | 0 | 15184 | 15184 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-13 | Completed |  |  | GAD 2024 | DO MOOE
| SUPPLIES for the 1st Quarter CY 2026 for Legal Unit | LEGAL UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-03 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-13 | 2026-04-13 | Government of the Philippines (current year's budget) | 16350.62 | 16350.62 | 0 | 16223 | 16223 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-13 | Completed |  |  | GAD 2024 | DO MOOE
| TARPAULIN for the Launching of the 2026 National Women’s Month Celebration and the DepEd GAD Website Center | CID- PSDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 1250 | 1250 | 0 | 1240 | 1240 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Completed |  |  | GAD 2024 | GAD FUND
| FUEL for the consumption for the month of April- June 2026 | Supply Office | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-09 | 2026-06-09 | Government of the Philippines (current year's budget) | 149904 | 149904 | 0 | 141576 | 141576 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-09 | Completed |  |  | GAD 2024 | DO MOOE
| DRINKING WATER for the consumption for the Month of April- June 2026 | Supply Office | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-10 | 2026-06-10 | Government of the Philippines (current year's budget) | 9000 | 9000 | 0 | 9000 | 9000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-10 | Completed |  |  | LAA-10-24-1230 | DO MOOE
| EQUIPMENT for the NMRAA 2026 | PSDS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-23 | 2026-03-23 | Government of the Philippines (current year's budget) | 222500 | 222500 | 0 | 222500 | 222500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-23 | Completed |  |  | GAD Fund 202 | SPORTS FUND
| POLO SHIRT for Participation in the REGIONAL SCHOOL PRESS CONFERENCE (RSPC) 2026 at Balingasag, Misamis Oriental | CID | No | Direct Contracting | N/A | 2026-03-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-11 | 2026-03-11 | Government of the Philippines (current year's budget) | 30500 | 30500 | 0 | 30500 | 30500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-11 | Completed |  |  | GAD Fund 2024 Continuing,ARH and Div. MOOE | REG. FEE
| POLO SHIRT for Participation in the REGIONAL FESTIVAL OF TALENTS (RFOT) 2026 at Balingasag, Misamis Oriental | CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-11 | 2026-03-11 | Government of the Philippines (current year's budget) | 139400 | 139400 | 0 | 139400 | 139400 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-11 | Completed |  |  | DIVISION MOOE | REG.FEE
| FOOD STUFF for the Orientation and Workshop on Learners Registry and Tracking System for School Heads and School Based AO II | ITO | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-09 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-03-24 | 2026-03-24 | Government of the Philippines (current year's budget) | 100800 | 100800 | 0 | 100800 | 100800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-03-24 | Completed |  |  | DIVISION MOOE | SCHOOL MOOE
| SUPPLIES for the DSAC in NMRAA | PSDS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-11 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 4670 | 4670 | 0 | 4670 | 4670 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | lgu fund | SPORTS FUND
| EQUIPMENT for the School Titling Operations | LEGAL UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-17 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-30 | 2026-04-30 | Government of the Philippines (current year's budget) | 49990 | 49990 | 0 | 49990 | 49990 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | Completed |  |  | MOOE 2024 | DO MOOE
| SUPPLIES for the CID for the Year 2026 | CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-17 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-10 | 2026-06-10 | Government of the Philippines (current year's budget) | 297620.84 | 297620.84 | 0 | 171987 | 171987 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-10 | Completed |  |  | LAA-10-25-177 | DO MOOE
| SUPPLIES for the CY 2026 1st Quarter of SGOD Office | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-17 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-03 | 2026-06-03 | Government of the Philippines (current year's budget) | 196143.13 | 196143.13 | 0 | 116746.79 | 116746.79 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-03 | Completed |  |  | LAA-10-25-177 | DO MOOE
| FOOD STUFF for the Division Federated Supreme Secondary Learner Government (SSLG) and Supreme Elementary Learner Government (SELG) Elections | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-18 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 23275 | 23275 | 0 | 23275 | 23275 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | LAA-10-25-177 | LAA-10-26-0047
| SUPPLIES for the Cashier Unit | CASHIER | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-19 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 22142.74 | 22142.74 | 0 | 8429 | 8429 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | School MOOE | DO MOOE
| SUPPLIES for the ICT Unit | IT | No | NP-53.9 - Small Value Procurement | N/A | 2026-03-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-30 | 2026-04-30 | Government of the Philippines (current year's budget) | 15164.74 | 15164.74 | 0 | 15023 | 15023 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-30 | Completed |  |  |  | DO MOOE
| FUEL for the month of April- June 2026 | Supply Office | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-01 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-09 | 2026-06-09 | Government of the Philippines (current year's budget) | 149981 | 149981 | 0 | 149981 | 149981 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-09 | Completed |  |  | LAA-10-24-279 &LAA-10-24-874/ | DO MOOE
| FOOD STUFF for the Conduct of weekly Division Executive Committee Meeting in April- June 2026, 8:30 AM at the Division Office Conference Hall | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-01 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 19-05-2026 | 19-05-2026 | Government of the Philippines (current year's budget) | 48750 | 48750 | 0 | 48750 | 48750 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 19-05-2026 | Completed |  |  | GAD 2024 | DO MOOE
| MEDICAL SUPPLIES for Palarong Pambansa Athletes | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-06 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-06 | 2026-04-06 | Government of the Philippines (current year's budget) | 25000 | 25000 | 0 | 24460 | 24460 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-06 | Completed |  |  | GAD 2024 | LAA-10-25-645
| EQUIPMENT for the In house printing, binding and delivery of structured, Pedagogy Lesson Guides and Learning packets | LRMDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-06 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-17 | 2026-06-17 | Government of the Philippines (current year's budget) | 11000 | 11000 | 0 | 8790 | 8790 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-17 | Completed |  |  | LAA-10-24-1230 | LAA-10-26-0012
| SUPPLIES for the Records Unit | RECORDS UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-06 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-16 | 2026-06-16 | Government of the Philippines (current year's budget) | 16095.36 | 16095.36 | 0 | 15612 | 15612 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-16 | Completed |  |  | Division MOOE | DO MOOE
| SUPPLIES for the Personnel Unit | PERSONNEL UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-06 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-23 | 2026-06-23 | Government of the Philippines (current year's budget) | 47753.07 | 47753.07 | 0 | 47728.45 | 47728.45 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-23 | Completed |  |  | LAA-10-25-17 | DO MOOE
| SUPPLIES for the Admin Unit | ADMIN UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-06 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-10 | 2026-06-10 | Government of the Philippines (current year's budget) | 16672.35 | 16672.35 | 0 | 16672.35 | 16672.35 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-10 | Completed |  |  | LAA-10-25-17 | DO MOOE
| EQUIPMENT for the LRP records safekeeping purposes | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-08 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-30 | 2026-06-30 | Government of the Philippines (current year's budget) | 10000 | 10000 | 0 | 9630 | 9630 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | Completed |  |  | Division MOOE | SUB-ARO-10-25-626
| FOOD STUFF for the First Quarterly Meeting For Administrative Officer II And Notice Of Meeting For Drivers, Utility Workers And Security Guards | ADMIN UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-13 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-02 | 2026-06-02 | Government of the Philippines (current year's budget) | 40000 | 40000 | 0 | 40000 | 40000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-02 | Completed |  |  | Division MOOE | DIVISION MOOE
| SUPPLIES for the School Division Office Payroll Processing | PAYROLL | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-06 | 2026-05-06 | Government of the Philippines (current year's budget) | 37876 | 37876 | 0 | 37876 | 37876 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-06 | Completed |  |  | School MOOE | SCHOOL MOOE
| FOOD STUFF for the Pre – Work on the Orientation on Promoting Drug and Smoke Free Schools and Worksplaces cum MOA Signing- | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-21 | 2026-04-21 | Government of the Philippines (current year's budget) | 15000 | 15000 | 0 | 15000 | 15000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-21 | Completed |  |  | GAD 2024 | DO MOOE Continuing
| FOOD STUFF for the Training of Teaching and Teaching- Realated Personnel on the Alignment of Classroom and National Assessments- | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-11 | 2026-05-11 | Government of the Philippines (current year's budget) | 360000 | 360000 | 0 | 360000 | 360000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-11 | Completed |  |  | FLO-ADM/LAA-10-25-108 | HRD FUND
| SUPPLIES for the Training of Teaching and Teaching- Realated Personnel on the Alignment of Classroom and National Assessments- | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-04 | 2026-06-04 | Government of the Philippines (current year's budget) | 38385 | 38385 | 0 | 36455 | 36455 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-04 | Completed |  |  | FLO-ADM/LAA-10-25-108 | HRD FUND
| FOOD STUFF for the Prework:Training of Teaching and Teaching- Realated Personnel on the Alignment of Classroom and National Assessments | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-05 | 2026-05-05 | Government of the Philippines (current year's budget) | 18000 | 18000 | 0 | 18000 | 18000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-05 | Completed |  |  | Division MOOE 2024 | HRD FUND
| FOOD STUFF for the Postwork:Training of Teaching and Teaching- Realated Personnel on the Alignment of Classroom and National Assessments | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-18 | 2026-05-18 | Government of the Philippines (current year's budget) | 18000 | 18000 | 0 | 18000 | 18000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-18 | Completed |  |  |  | HRD FUND
| TARPAULIN for the Training of Teaching and Teaching- Realated Personnel on the Alignment of Classroom and National Assessments- | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-11 | 2026-05-11 | Government of the Philippines (current year's budget) | 864 | 864 | 0 | 3870 | 3870 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-11 | Completed |  |  | FLO-ADM/LAA-10-25-108 | HRD FUND
| SUPPLIES for the Reproduction of Learning Sheet (LAS) | ALS | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-07 | 2026-05-07 | Government of the Philippines (current year's budget) | 56104 | 56104 | 0 | 56104 | 56104 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-07 | Completed |  |  |  | SUB-ARO-10-26-0230
| SUPPLIES for the 2nd Quarter Office Supplies for the Office of ASDS | ASDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-16 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-02 | 2025-11-14 | Government of the Philippines (current year's budget) | 18889.96 | 18889.96 | 0 | 18889.96 | 18889.96 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2025-11-14 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | DO MOOE
| MATERIALS for the New Division Office grounds at DepEd Park, Civoleg, Brgy. Lunotan | SEPS- SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-21 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-09 | 2026-06-09 | Government of the Philippines (current year's budget) | 13400 | 13400 | 0 | 13400 | 13400 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-09 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | DO MOOE
| FOOD STUFF for the Participants of Liquidation Day for the Months of January- March 2026- | ACCOUNTING | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-21 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-04-23 | 2026-04-23 | Government of the Philippines (current year's budget) | 38250 | 38250 | 0 | 38250 | 38250 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-04-23 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | SCHOOL MOOE
| FOOD STUFF for the Division Training on the Revised Grades 6,9,10 Curriculum (Grades 9 and 10) | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-22 | 2026-05-22 | Government of the Philippines (current year's budget) | 786600 | 786600 | 0 | 786600 | 786600 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-22 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | HRTD CONTINUING FUNDS
| FOOD STUFF for the Division Training on the Revised Grades 6,9,10 Curriculum (Grades 6) | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-29 | 2026-05-29 | Government of the Philippines (current year's budget) | 545400 | 545400 | 0 | 4590 | 4590 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-29 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | HRTD CONTINUING FUNDS
| SUPPLIES for the Division Training on the Revised Grades 6,9,10 Curriculum | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-08 | 2026-06-08 | Government of the Philippines (current year's budget) | 161249 | 161249 | 0 | 161249 | 161249 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-08 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | HRTD CONTINUING FUNDS
| FOOD STUFF for the Training Workshop for School Heads and Learner Formation Officers (LFO) on the Implementing Rules and Regulations (IRR) of RA 10627 otherwise known as the Anti- Bullying Act of 2013 and its revised IRR- | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-04 | 2026-06-04 | Government of the Philippines (current year's budget) | 125400 | 125400 | 0 | 125400 | 125400 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-04 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | GAA 2025
| SUPPLIES for the Training Workshop for School Heads and Learner Formation Officers (LFO) on the Implementing Rules and Regulations (IRR) of RA 10627 otherwise known as the Anti- Bullying Act of 2013 and its revised IRR | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-03 | 2026-06-03 | Government of the Philippines (current year's budget) | 11995 | 11995 | 0 | 11095 | 11095 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-03 | Completed |  |  | LAA-10-25-222/LAA-10-24-1034 | GAA 2025
| TARPAULIN for the Training Workshop for School Heads and Learner Formation Officers (LFO) on the Implementing Rules and Regulations (IRR) of RA 10627 otherwise known as the Anti- Bullying Act of 2013 and its revised IRR | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-03 | 2026-06-03 | Government of the Philippines (current year's budget) | 1280 | 1280 | 0 | 1280 | 1280 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-03 | Completed |  |  | HRTD 2024 | GAA 2025
| TARPAULIN for the Division Training on the Revised Grades 6,9,10 Curriculum | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-08 | 2026-06-08 | Government of the Philippines (current year's budget) | 1056 | 1056 | 0 | 1056 | 1056 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-08 | Completed |  |  | HRTD 2024 | HRTD FUNDS
| TARPAULIN for the Training of Teaching and Teaching Related Personnel on the Alignment of Classroom and National Assessment | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-11 | 2026-05-11 | Government of the Philippines (current year's budget) | 1056 | 1056 | 0 | 1056 | 1056 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-11 | Completed |  |  | HRTD 2024 | HRTD FUNDS
| FOOD STUFF for the Prework: Division Training on the Revised Grades 6,9,10 Curriculum (Grades 9 and 10) | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2025-09-23 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-08 | 2026-05-08 | Government of the Philippines (current year's budget) | 45000 | 45000 | 0 | 45000 | 45000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-08 | Completed |  |  | HRTD 2024 | HRTD CONTINUING FUNDS
| SNACKS for the Turnover Ceremony of Boxing Ring | PSDS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-04-29 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-17 | 2026-05-17 | Government of the Philippines (current year's budget) | 7500 | 7500 | 0 | 7500 | 7500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-17 | Completed |  |  |  | SPORTS FUND
| FOOD STUFF for the Developing Core Communication Skills for Non- Teaching Personnel | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-08 | 2026-05-08 | Government of the Philippines (current year's budget) | 122400 | 122400 | 0 | 122400 | 122400 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-08 | Completed |  |  | SUB-ARO -10-25-014 | LAA-10-25-1086
| TARPAULIN for the Developing Core Communication Skills for Non- Teaching Personnel | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-08 | 2026-05-08 | Government of the Philippines (current year's budget) | 1056 | 1056 | 0 | 1056 | 1056 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-08 | Completed |  |  | GAD 2024 | LAA-10-25-1086
| SUPPLIES for the Developing Core Communication Skills for Non- Teaching Personnel | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-04 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-11 | 2025-10-30 | Government of the Philippines (current year's budget) | 3440.6 | 3440.6 | 0 | 3440.6 | 3440.6 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2025-10-30 | Completed |  |  | LAA-10-24-372 | LAA-10-25-1086
| SUPPLIES for the 2ND Quarter of 2026 for COA use | COA | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-07 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-10 | 2026-06-10 | Government of the Philippines (current year's budget) | 9368.03 | 9368.03 | 0 | 7673.5 | 7673.5 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-10 | Completed |  |  | OSEC-10-25-01937 | Division MOOE/
| FURNITURE for the 2ND Quarter of 2026 for COA use | COA | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-07 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-07-06 | 2026-07-06 | Government of the Philippines (current year's budget) | 22800 | 22800 | 0 | 17560 | 17560 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-06 | Completed |  |  |  | Division MOOE/
| FOOD STUFF for the Training Workshop on Enhancing Research Coaching Competencies of High School Science Teacher | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-07 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-04 | 2026-06-04 | Government of the Philippines (current year's budget) | 27000 | 27000 | 0 | 27000 | 27000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-04 | Completed |  |  |  | HRTD CONTINUING FUNDS
| SUPPLIES for the Training Workshop on Enhancing Research Coaching Competencies of High School Science Teacher | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-07 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-17 | 2026-06-17 | Government of the Philippines (current year's budget) | 6700 | 6700 | 0 | 6700 | 6700 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-17 | Completed |  |  | OSEC-10-25-01032 | HRTD CONTINUING FUNDS
| FOOD STUFF for the Conduct of Division Management Committee Meeting in May | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-07 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-05 | 2026-06-05 | Government of the Philippines (current year's budget) | 63000 | 63000 | 0 | 63000 | 63000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-05 | Completed |  |  | Division MOOE | SCHOOL/DO MOOE
| FOOD STUFF for the Orientation and Workshop on Esf7 for all School Heads | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-07 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-11 | 2026-05-11 | Government of the Philippines (current year's budget) | 52650 | 52650 | 0 | 52650 | 52650 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-11 | Completed |  |  | LAA-10-24-888, LAA-10-24-690/ | SCHOOL MOOE
| FOOD STUFF for the Condcut of Relocation Survey and Soil Exploration at Pundasan NHS new school site | LEGAL UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-11 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-19 | 2026-05-19 | Government of the Philippines (current year's budget) | 14800 | 14800 | 0 | 14800 | 14800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-19 | Completed |  |  | LAA-10-24-888, LAA-10-24-690/ | OSEC-10-26-02097
| TARPAULIN for the NMRAA Convergence and NSAC Screening of Athletes and Validation of Documents | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-11 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-09 | 2026-06-09 | Government of the Philippines (current year's budget) | 10660 | 10660 | 0 | 10660 | 10660 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-09 | Completed |  |  | Division MOOE | SPORTS FUND
| SUPPLIES for the Establishment of Learner Rights and Protection Desk (LRPD) and Mental Wellness Space for Learner Athletes | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-11 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-07-07 | 2026-07-07 | Government of the Philippines (current year's budget) | 48996 | 48996 | 0 | 48478 | 48478 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-07-07 | Completed |  |  |  | 2025 MOOE/GAD CONTINUING
| MATERIALS for the Provident Transaction and files | ACCOUNTING | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-11 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-30 | 2026-06-30 | Government of the Philippines (current year's budget) | 91000 | 91000 | 0 | 39650 | 39650 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-30 | Completed |  |  | LAA-10-25-147 | provident fund
| SUPPLIES for the Division Level Cascading of the Regional Reorientation on Alternative Delivery Modes (ADM) | CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-11 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-10 | 2026-06-10 | Government of the Philippines (current year's budget) | 6687 | 6687 | 0 | 6687 | 6687 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-10 | Completed |  |  | LAA-10-25-147 | SUB-ARO-10-25-588
| TARPAULIN for the Division Level Cascading of the Regional Reorientation on Alternative Delivery Modes (ADM)- | CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-11 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-10 | 2026-06-10 | Government of the Philippines (current year's budget) | 1056 | 1056 | 0 | 1056 | 1056 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-10 | Completed |  |  |  | SUB-ARO-10-25-588
| FOOD STUFF for the Regional Office Personnel during Division Visits | PSDS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-14 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-18 | 2026-05-18 | Government of the Philippines (current year's budget) | 10500 | 10500 | 0 | 10500 | 10500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-18 | Completed |  |  | LAA-10-25-147 | DO MOOE
| FOOD STUFF for the Peronnel from the Department of Agriculture for the conduct of Soil Testing at Kalipay NHS on May 26, 2026 | EPS- CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-18 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-05-26 | 2026-05-26 | Government of the Philippines (current year's budget) | 2000 | 2000 | 0 | 2000 | 2000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-05-26 | Completed |  |  | MED Fund/ sub-aro-10-24-429 | DO MOOE
| PRINTING AND DELIVERY of Reading Materials for Key Stage 1 Learners | EPS- LRMDS | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-19 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 1517438 | 1517438 | 0 | 1020407 | 1020407 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | MED Fund/ sub-aro-10-24-429 | LAA-10-25-311
| MATERIALS for the Building Partnerships and Linkages Program for SY: 2025-2026 advocacies, recognition of education partners/ stakeholders and monitoring of the implementation | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-25 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 16280 | 16280 | 0 | 16280 | 16280 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | MED Fund/ sub-aro-10-24-429 | OSEC-10-26-1774
| FOOD STUFF for the Division Level Cascading of the Regional Reorientation on Alternative Delivery Modes | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-05-28 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-25 | 2026-06-25 | Government of the Philippines (current year's budget) | 104000 | 104000 | 0 | 104000 | 104000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-25 | Completed |  |  | MED Fund/ sub-aro-10-24-429 | SUB-ARO-10-25-580
| FOOD STUFF for the Brigada Opisina Activity | ADMIN UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-01 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-15 | 2026-06-15 | Government of the Philippines (current year's budget) | 24000 | 24000 | 0 | 24000 | 24000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-15 | Completed |  |  | MED Fund/ sub-aro-10-24-429 | Trust Fund
| SUPPLEMENTARY LEARNING RESOURCES FOR THE SCHOOL LIBRARIES | LRMDS | No | Direct Contracting | N/A | 2026-06-01 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 425973 | 425973 | 0 | 425973 | 425973 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | MED Fund/ sub-aro-10-24-429 | SUB-ARO-10-25-354
| FOOD STUFF for the Child and Adolescent Risk Screener Training | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-02 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 539250 | 539250 | 0 | 539250 | 539250 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Completed |  |  | MED Fund/ sub-aro-10-24-429 | GAD FUNDS
| fSUPPLIES for the Child and Adolescent Risk Screener Training | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-02 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 37300 | 37300 | 0 | 37300 | 37300 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Re schedule the date |  |  |  | GAD Continuing Funds
| TARPAULIN for the Child and Adolescent Risk Screener Training | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-02 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 800 | 800 | 0 | 800 | 800 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Re schedule the date |  |  |  | GAD Continuing Funds
| SUPPLIES for Payroll Processing - 2nd Quarter Supplies | PAYROLL | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-09 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 43189.32 | 43189.32 | 0 | 19441 | 19441 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  |  |  |  | MED Fund/ sub-aro-10-24-429 | DO/SCHOOL MOOE
| FUEL CONSUMPTION for the month of July- September 2026 | ADMIN UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 140000 | 140000 | 0 | 138600 | 138600 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | MED Fund/ sub-aro-10-24-429 | DO MOOE
| DRINKING WATER for the Month of July- September 2026- | ADMIN UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 9000 | 9000 | 0 | 9000 | 9000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | MED Fund/ sub-aro-10-24-429 | DO MOOE
| FOOD STUFF for the Alternative Learning System (ALS) Graduation | ALS | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-23 | 2026-06-23 | Government of the Philippines (current year's budget) | 30000 | 30000 | 0 | 30000 | 30000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-23 | Completed |  |  | MED Fund/ sub-aro-10-24-429 | FLO ALS- 230/189/580/
| SUPPLIES for the 1st Quarter CY 2026 | Supply Office | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 33200 | 33200 | 0 | 10772 | 10772 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | MED Fund/ sub-aro-10-24-429 | DO MOOE
| FOOD STUFF for the SBFP Orientation SY 2026- 2027 | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 246000 | 246000 | 0 | 246000 | 246000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | Divisiom mooe 2025 | SUBA-ARO-10-26-0377
| FOOD STUFF for the SBFP Quarterly Meeting SY 2026- 202 | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 135000 | 135000 | 0 | 135000 | 135000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | Divisiom mooe 2025 | SUBA-ARO-10-26-0377
| FOOD STUFF for the SBFP Program Implementation Review SY 2026- 2027 | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 67500 | 67500 | 0 | 67500 | 67500 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | Divisiom mooe 2025 | SUBA-ARO-10-26-0377
| TARPAULIN for the SBFP Implementation SY 2026- 2027 | SHNU | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-15 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  |  |  | Government of the Philippines (current year's budget) | 4000 | 4000 | 0 | 4000 | 4000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A |  | Ongoing Procurement Process |  |  | Divisiom mooe 2025 | SUBA-ARO-10-26-0377
| FOOD STUFF for the Coordination Meeting with Stakeholders and Partners on the Implementation of the three term School Calendar in Basic Education | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-16 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-17 | 2026-06-17 | Government of the Philippines (current year's budget) | 2250 | 2250 | 0 | 2250 | 2250 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-17 | Completed |  |  | LAA-10-24-223/ | Local funds
| ACCOMMODATION AND FOOD STUFF for the Monitoring and Evaluation of the actual administration of the Language Identification Tool (LIT) Model during the administration of Language Mapping Process to selected schools in Gingoog City Division including multigrade and IP schools with Regional and Central Office Monitoring Personne | EPS-CID | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-18 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-22 | 2026-06-22 | Government of the Philippines (current year's budget) | 12700 | 12700 | 0 | 12700 | 12700 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-22 | Completed |  |  |  | LAA-10-25-866
| TARPAULIN AND ADVOCACY T-SHIRT for the Provision of Printed Advocacy Material for The Division Personnel and Barangay 26 Officials for The Tree Growing Activity at Gahub Riverbank in Line with The Arbor Day 2026 Celebration | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-22 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-25 | 2026-06-25 | Government of the Philippines (current year's budget) | 37500 | 37500 | 0 | 34150 | 34150 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-25 | Completed |  |  | SUB ARO-10-24-429 | LAA-10-25-683
| FOOD STUFF for the Provision of Printed Advocacy Material for The Division Personnel and Barangay 26 Officials for The Tree Growing Activity at Gahub Riverbank in Line with The Arbor Day 2026 Celebration | SGOD | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-22 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-25 | 2026-06-25 | Government of the Philippines (current year's budget) | 20720 | 20720 | 0 | 20720 | 20720 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-25 | Completed |  |  | Division MOOE 2024 | LAA-10-25-683
| FOOD STUFF for the Special Meeting with the Regional Office Personnel | PERSONNEL UNIT | No | NP-53.9 - Small Value Procurement | N/A | 2026-06-22 |  | N/A | N/A | N/A |  | N/A | N/A | N/A |  |  |  | N/A | N/A | N/A |  |  | 2026-06-26 | 2026-06-26 | Government of the Philippines (current year's budget) | 2000 | 2000 | 0 | 2000 | 2000 | 0 |  | N/A | N/A | N/A | N/A | N/A | N/A | 2026-06-26 | Completed |  |  | Division MOOE 2024 | DO MOO3
-
[25 empty] | Total Allotted Budget of Procurement Activities | 11265906.12 | 11265906.12 | 0 |  |  |  | 13.02%
[25 empty] | Total Contract Price of Procurement Activities Conducted |  |  |  | 9799137.61 | 9799137.61 | 0
[23 empty] | Total Savings (Total Allotted Budget - Total Contract Price) |  |  | 1466768.51 | [14 empty] | 2023-06-30
Code (PAP) | Procurement Project | PMO/End-User | Is this an Early Procurement Activity? | Mode of Procurement | Pre-Proc Conference | Ads/Post of IB | Ave. No. of Days to Commence Procurement (Pre-Proc to Posting of IB) (i.3) | Pre-bid Conf | Eligibility Check | Sub/Open of Bids | Average No. of Days to open bid proposals (Posting of IB to Opening of Bids) (i.4) | Bid Evaluation | Post Qual | Date of BAC Resolution Recommending Award | Accumulated Days in Evaluation of Bids (Opening of Bids to Post Qua) | Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) (i.5) | Average Number of Days to Conclude Procurement (IB to BAC Reso) (i.6) | Notice of Award | Contract Signing | Notice to Proceed | Average Number of Days to Issue Notice to Proceed (NOA to NTP) (i.7) | Average Days from (Posting of IB to NTP) (i.8) | Delivery/ Completion | Inspection & Acceptance | Source of Funds | Total | MOOE | CO | Total2 | MOOE2 | CO3 | % Variance | List of Invited Observers | Pre-bid Conf4 | Eligibility Check5 | Sub/Open of Bids6 | Bid Evaluation7 | Post Qual8 | Delivery/ Completion/ Acceptance (If applicable) | Remarks (Explaining changes from the APP) | Column42
ONGOING PROCUREMENT ACTIVITIES | [31 empty] | -
-
[7 empty] | #DIV/0! | [17 empty] | Total Allotted Budget of On-going Procurement Activities | 0 | 0 | 0 | 0 | 0 | 0 | #DIV/0!
|  | Prepared by: | [9 empty] | Recommended for Approval by: | [16 empty] | APPROVED:
|  | MA. ANGELOU G. SABANTO | [9 empty] | MYRON GIL D. TALOGIS, CESE | [16 empty] | EDGARDO V. ABANIL, CESO V
|  | BAC Secretariat | [9 empty] | BAC Chairperson | [16 empty] | Head of the Procuring Entity

## Tool 1-Processing (hidden)
Summary of Information for Processing of IRPP
Indicator 1: % of Processed Procurement Activities vs Planned in terms of amount |  | #REF!
Formula | Value | Remarks
Total Amount of APP as updated | #REF!
Divide by: Total Amount of ABC of procurement activities started | #REF! | ABC of awarded + ABC of on-going procurement projects (less ABC of Failure of Bids)
Indicator 2: Average % of Variance Between Contract Amount vs Approved Budget for the Contract |  | 0%
Particular | Value | Remarks
Total Amount of ABC of procurement activities started | #REF!
Total Contact Cost | 0
Total Variance for Each Awarded Procurement Project | #REF! | Column shall be hidden
Divide by Number of Awarded Procurement Projects | 0
Indicator 3. Timeliness on the Conduct of Procurement
|  | Indicator 3.1 Average No. of Days to commence procurement (Pre-Proc to Posting of IB) |  | Indicator 3.2: Average No. of Days to open bid proposals (Posting of IB/ to Opening of Bids) |  | Indicator 3.3: Average Number of Days to Recommend Award (Opening of Bids to Recommend Award) |  | Indicator 3.4: Average Number of Days to Conclude Procurement (Posting of IB to Recommend Award) |  | Indicator 3.5: Average Number of Days to Issue Notice to Proceed (from Issuance of NOA to Issuance of NTP) |  | Indicator 3.6: Accumulated Number of Days for the Procurement Process (Posting of IB to NTP)
Mode of Procurement | Total No. of Activities under subject modality | Total No. of Days from PreProc to IB | Average Days from Pre-Proc to Posting of IB | Total No. of Days from IB to Opening | Average Days from Posting of IB to Opening of Bids | Total No. of Days Opening to Recommend Award) | Average Days from Opening of Bids to Recommend Award | Total No. of Days from Posting of IB to Recommend Award | Average Days from Posting of IB to Recommend Award | Total No. of Days from Issuance of NOA to Issue NTP | Average Days from NOA to NTP | Total No. of Days from Posting of IB to Issue NTP | Average Days from Posting of IB to NTP
Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Limited Source Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Direct Contracting | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Repeat Order | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.1 Two Failed Biddings | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.2 Emergency Cases | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.3 Take-Over of Contracts | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.5 Agency-to-Agency | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.7 Highly Technical Consultants | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.9 - Small Value Procurement | 127 | 0 | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
NP-53.10 Lease of Real Property and Venue | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.11 NGO Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.12 Community Participation | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Emergency Procurement under Bayanihan Act | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Foreign Guidelines - Alternative Method | 0 | 0 |  | 0 |  | 0 |  | 0 |  | 0 |  | 0
Total | 130 | 0 | 0 | 0.78261 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
*formula for days interval for each procurement activity for each indicator are embedded in the PMR.
Indicator 4. Percentage of Amount and Volume by Tender and Award of Procurement Activities per Mode of Procurement
Mode of Procurement | Total No. of Activities | Total Number of Awarded | Total ABC | Total Contract Cost | %Vol of Awarded | %ABC of Awarded | Total Number of Failed | ABC of Failed
Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Limited Source Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Direct Contracting | 3 | 0 | 0 | 0 | 0% |  | 0 | 0
Repeat Order | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(a) - Unforeseen Contingency | 0 | 0 | 0 | 0 |  |  | 0 | 0
Shopping 52.1(b) - Regular Office Supplies and Equipment no available in PS | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.1 Two Failed Biddings | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.2 Emergency Cases | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.3 Take-Over of Contracts | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.4 Adjacent or Contiguous | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.5 Agency-to-Agency | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.6 Scientific, Scholarly, Artistic Work, Exclusive Technology and Media Services | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.7 Highly Technical Consultants | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.8 Defense Cooperation Agreement | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.9 - Small Value Procurement | 128 | 0 | 0 | 0 | 0% |  | 11 | 872826
NP-53.10 Lease of Real Property and Venue | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.11 NGO Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.12 Community Participation | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.13 UN Agencies, Int'l Organizations or International Financing Institutions | 0 | 0 | 0 | 0 |  |  | 0 | 0
NP-53.14 Direct Retail Purchase of Petroleum Fuel, Oil and Lubricant (POL) Products and Airline Tickets | 0 | 0 | 0 | 0 |  |  | 0 | 0
Emergency Procurement under Bayanihan Act | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Competitive Bidding | 0 | 0 | 0 | 0 |  |  | 0 | 0
Foreign Guidelines - Alternative Method | 0 | 0 | 0 | 0 |  |  | 0 | 0
Total | 131 | 0 | 0 | 0 | 0% | #DIV/0! | 11 | 872826
Total for Alternative Mode of Procurement | 131 | 0 | 0 | 0 | 0% | #DIV/0! | 11 | 872826
Indicator 5: Accumulated No. of Days for On-going Procurement Activities
Timeline | No. of Procurement Activities | %
Exceeds 180 days | 0 | 0%
Within 91 to 180 days | 0 | 0%
Within 45 to 90 days | 0 | 0%
Within 0 to 44 days | 0 | 0%
Total | 0 | 0%
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 6. Distribution of On-going, Awarded, and Failed procurement Activities
Status | No. of Procurement Activities | % by No. of Procurement of Activities | ABC Amount of Activities | % by ABC | Contract Cost | Contract/ABC | Variance
Awarded | 0 | 0% | 0 | 0% | 0 | 0% | #DIV/0!
Completed | 112 | 81.75% | 8429639.06 | 70.43% | 7522130.61 | 71.52% | 0.10766
Failed | 10 | 7.299% | 828926 | 6.925% | 820002 | 7.796% | 0.010766
Ongoing | 15 | 10.95% | 2711077.74 | 22.65% | 2175566 | 20.68% | 0.19753
Total | 137 | 100% | 11969642.8 | 100% | 10517698.61 | 100% | 0.1213
*Validation shall be provided for the PMR so that the PMO can easily select and determined the total count
Indicator 7a: % of Number of Procurement activities conducted under early procurement |  |  | 0%
Indicator 7b: % of ABC of Procurement activities conducted under early procurement |  |  | 0%
Particular | No. of Procurement Activities | ABC Amount of Activities
Under EPA | 0 | 0
Regular Procurement | 130 | 11222006.12
Total | 130 | 11222006.12
Indicator 8a: Percentage of Number of Awarded Contracts under EPA |  |  | 0%
Indicator 8b: Percentage of Contract Cost of EPA against the total ABC under EPA |  |  | 0%
Formula | No. of Procurement Activities | Amount of ABC Procurement Activities | Contract Cost of Procurement Activities | Percentage Variance
Total Contracts Awarded under EPA* | 0 | 0 | 0 | 0%
Total Contracts Completed under EPA* | 0 | 0 | 0 | 0%
Total Failed Bid under EPA* | 0 | 0 | 0 | 0%
Total Ongoing Activities under EPA* | 0 | 0 | #VALUE! | #VALUE!
Total Procurement Activities under EPA | 0 | 0 | #VALUE!
To compute for the total, a separate sheet may be created of the PMO may simply filter the cells to capture the total number.
Indicator 9: Stages where failure of bidding are encountered
Particular | No. of Procurement Activities | Amount of ABC | Vol. % | Amount %
Invitation To Bid | 0 | 0 | 0% | 0%
Pre-bidding Conference | 7 | 500821 | 70% | 60.42%
Opening of Bids | 3 | 328105 | 30% | 39.58%
Bid Evaluation | 0 | 0 | 0% | 0%
Post-Qualification | 0 | 0 | 0% | 0%
BAC Resolution | 0 | 0 | 0% | 0%
Award | 0 | 0 | 0% | 0%
Cancelled | 0 | 0 | 0% | 0%
TOTAL | 10 | 828926

## Validation Menu (hidden)
REMARKS | STATUS | STAGE OF PROCUREMENT | Source of Funds
Awarded with issued Notice of Award | Awarded | Invitation To Bid | Government of the Philippines (current year's budget)
Completed | Completed | Pre-bidding Conference | Government of the Philippines (continuing budget)
Ongoing Procurement Process | Failed | Opening of Bids | Government of the Philippines (current year's and continuing budget)
Failed under Section 32.2.1 (a) | Ongoing | Bid Evaluation | Grant by an International Financing Institution
Failed under Section 35.1 (a) |  | Post-Qualification | Loan from an International Financing Institution
Failed under Section 35.1 (b) |  | BAC Resolution
Failed under Section 35.1 (c) |  | Award
Failed under Section 41 (b) |  | Cancelled
Failed under Section 41 (c)
Contract was extended
Contract was renewed
Cancelled
Others, please encode directly on the cell